## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | M.Rohit | 2025-10-07 | Model fails to detect helmets in night mode | Sprint 1 | M. Rohit | Logical | Adjusted thresholds | 2025-10-09 | Closed | Improved accuracy
2 | M.Rohit | 2025-10-12 | OCR misreads license plate | Sprint 2 | M. Rohit | Standards | Re-trained OCR model | 2025-10-15 | Closed | Improved reliability
3 | M.Rohit | 2025-10-20 | Dashboard not displaying live feed | Sprint 2 | M. Rohit | User Interface | Fixed Flask route | 2025-10-21 | Closed | Verified
4 | M.Rohit | 2025-10-25 | Delay in result processing | Sprint 3 | M. Rohit | Maintainability | Optimized image loop | 2025-10-27 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others